## active build legal
Property / matter | Last known status | What needs follow-up | Risk | Status | NOTES (3/30) | NOTES (3/31) | NOTES (04/15)
Lot 29, 26 Windermere Rd, Lochinvar | Bao chased settlement + finance. Chris said approval was still pending at one point; builder/PM onboarding also started later. Prior update indicated OC expected in 4–8 weeks. | Confirm finance fully cleared, settlement status, and whether OC timeline is still current. | High | Open
Lot 71, 26 Windermere Rd, Lochinvar | Mixed/delayed builder updates earlier; one update said OC expected 28/03. | Confirm whether OC actually issued and whether handover occurred. | High | Open / verify
Lot 54, Windermere Rd, Lochinvar | Client escalated because photos/progress info didn’t match property; Ethan later admitted wrong property was inspected and said Bathla was being asked for correct photos. | Send client a clean factual update with correct property status, photos, and revised completion timing. | High | Open
Lot 20 Myee Loop, Wollert | Legal/contract confusion around Lot 2 vs Unit 20, plus bare trust / contract detail chase. | Confirm final contract identifiers and make sure legal + finance docs match the actual lot/unit. | High | Open |  |  | Waiting for Vals
Lot 924 Beedelup Court / 924 Claravale, Hilbert | Land rego pushed to June; finance/settlement/deposit threads active. | Confirm revised rego month, settlement readiness, invoice/deposit status. | High | Open
64A Ryans Road, Gillieston Heights | In January, sellers confirmed it was not registered and never marketed as registered; later thread suggested late Apr / early May settlement. | Confirm if registration happened and whether settlement is now booked/completed. | High | Open | 3/30 |  | Council has signed off. They’re now waiting for the subdivision certificate to be issued, then it will go to LRS for title registration. Delay is due to council taking longer than expected.
Lot 105 Aldeia, Logan Reserve | Builder update said Form 11 not yet issued; OC/handover being chased. | Confirm Form 11 issue date, handover date, and whether any defects/PC inspection remain. | High | Open | 3/30 FORM 11 ISSUED; APRIL 13 SETTLEMENT |  | Invoice to be issued
15/22 Eastbrook Links, Muswellbrook | Delays and timing confusion; January thread said slab pours expected early February; later update said piering done but trades not yet on site. | Confirm current build stage and whether timeline blew out again. | High | Open | 3/30 |  | 4/15
Lot 1414 Eastbrook Links, Muswellbrook | Bao chased vendor solicitor; waiting on vendor-signed exchanged contract. | Confirm exchanged contract received and whether settlement/build process progressed. | Medium-High | Open | 3/30 nothing is outstanding |  | transfer duty 5/12
Lot 721 / 919 / 915 Maroochy St, South Maclean cluster | Repeated construction delay/build update threads; one January update for 919MS said booking for 16 Jan. Later PM / inspection details were being requested around practical completion. | Check each lot separately for actual stage, PC inspection, PM allocation, and whether any remain stuck. | High | Open | 3/30 | ISSUED LETTER FROM Q HOMES | various stages
Lot 1031 Yapper Rd, South Maclean | Bao received HIA build contract in Jan; rego update still pending then. Later BA approval was being chased and expected “back end of next week” at one point. | Confirm land rego, BA, and build start status. | High | Open | 3/30 | ISSUED LETTER FROM Q HOMES; AWAITING BA | 4/15
Lot 225 Century Estate, Redbank Plains | Bao chased whether rego was still on track for 15 Jan; reply said they were seeking update from developers. Prior concern was avoiding a third finance application. | Confirm whether rego occurred and whether finance had to be re-run. | High | Open | REGO ON APR 15; WAIT TILL THEN |  | land rego pushed to August
Lot 177 Greenhaven Blvd / South Place, Deebing Heights | Settlement extension thread; Rosh confirmed it settled on 12/01/26. Separate client concern about updates/photos existed earlier. | Main risk now is post-settlement clean-up: build docs, client communication, next-stage builder items. | Medium | Mostly resolved, verify close-out | 3/30 | ISSUED LETTER FROM Q HOMES; BA RECEIVED; AWAITING CONSTRUCTION COMMENCEMENT LETTER; REQUEST FOR CLARIF RE: DELAYS & FINANCIAL SITUATION | 4/30 slab pour
Lot 18 Mali Way / 18 Manuka Rd, Logan Village | Bao chased slab update in January; prior thread indicated plumbing / approval delays. | Confirm building approval/slab timing and whether this progressed. | Medium-High | Open | 3/30
Lot 310 The Gardens, Lakelands | Tranche 2 invoicing/payment follow-up was active. | Confirm whether tranche payment cleared and whether file can be closed. | Medium | Verify | 3/30
340 The Gardens, Lakelands | In Jan, Bao chased build deposit timing before expected settlement; Locale replied they didn’t appear to have formal finance approval yet. Later indications suggested it may have moved on. | Confirm whether finance approval was eventually received and whether build deposit / settlement completed. | High | Open / verify | REQUEST FOR UPDATE APRIL FIRST WEEK (Last UD: Mar 23) |  | awaiting slab pour date
Lot 361 The Gardens, Lakelands (Walker & Jeffrey) | Jan legal thread said they had not received build contract or finance confirmation, with risk seller could pull out if no extension requested. Later this file surfaced as progressing toward settlement. | Confirm whether extension was required, whether finance/build contract completed, and if file is now fully settled. | High | Open / verify | AWAITING BA; REQUEST UPDATE APRIL FIRST WEEK |  | still awaiting BA
Lot 306 Elridge Estate, Jimboomba | Bao chased build update repeatedly. Chris said finance had already gone unconditional; later build was said to be midway through fit-off / landscaping underway, and Bao asked May to intro Oliver Hume PM. | Confirm practical completion / handover / PM setup / inspection. | High | Open | CLOSED
1975 Meridian Crescent, Flagstone | Bao chased rego again in Jan; later update said rego expected July. | Confirm whether rego timeline is still July or moved again. | Medium-High | Open | JUST KEEP AN EYE; REQUEST TIMELINE CONFIRMATION ON APRIL SECOND WEEK |  | Land rego on July
Lot 583 Rosella Circuit, Morayfield | Bao chased land rego in Jan; later thread indicated client travel / signing timing issues. | Confirm registration, signed docs, and whether deal has progressed. | Medium | Open | 3/30
1/3 Mary Street, Spotswood | Oliver Hume needed build contract, floorplan, builder, settlement date etc to proceed. | Confirm whether PM onboarding pack was completed. | Medium | Open | CLOSED
11 Hidcote Rd, Lakelands (Whiston) | Bao asked if build deposit invoice had been issued after land settlement; Alison said she needed settlement confirmation and didn’t yet see docs issued. Prior note said land had settled 16 Jan. | Confirm build deposit invoice, settlement docs, and whether builder file activated. | High | Open / likely partially complete
18 Oaklands Drive, Caboolture South | Early Jan thread said still waiting on final council tick; later Bao sent client update saying Oaklands Estate had now registered and settlement would follow 14 days later. | Confirm whether settlement actually completed and whether build moved forward. | High | Open / verify | 3/30
Lot 2663 / 75 Olympic Parade, Clyde | Mixed PM/access/warranty/fencing refund issues surfaced later. | Confirm who owns post-settlement defects / PM / reimbursement items. | Medium | Open
29 Currawong St, Preston VIC | Defect rectification escalation, poor builder communication, warranty timing concern. | Needs owner to continue pressure on builder and document rectification deadlines. | High | Open
73 Coorumbung Rd, Dora Creek | Client unresponsive to builder requests for council contribution / authority to commence. | Re-engage client and unblock authority/payment requirement. | Medium-High | Open
5 Cornerstone Place, Morayfield | Utility / water authority issue because builder contact still attached. | Confirm utility authority was transferred and file unblocked. | Medium | Open
9 Lacey Street, Camira | Urgent Jan issue: contract said registered / settling sooner than expected, so Bao requested extension to avoid finance penalty. Later internal note suggested all paid on tranche side. | Confirm land settlement, finance extension outcome, and whether build contract settled cleanly. | High | Open / verify | AWAITING FINANCE APPROVAL 03/30 |  | settlement occured, waiting for unconditional approval (FOLLOW UP NEXT WEEK)
Brooklands Private Estate – Stage 11 / DP 430010 | January update: slab did go down; Bao then chased whether slab invoice had been paid so next tranche commission could invoice. Earlier broader note said waiting on plate height / brickwork progress. | Confirm payment cleared and whether construction has materially progressed past slab. | Medium | Open
Lot 567 Jubilee Circuit, Hilbert | Payment / tranche thread likely resolved. | Quick close-out check only. | Low-Medium | Verify
Lot 1022 Isla Estate, Baldivis | Accounts confirmed Tranche 3 invoice INV-0440 was paid on 23 Dec 2025. | Likely can be closed unless any downstream builder issue remains. | Low | Likely resolved
390 Lake Valley Drive, Lakelands (Mediavillo & Ebriega) | Settlement due mid-Jan; Bao chased build deposit + building approval after settlement, but Locale said they hadn’t received formal finance approval. Later they asked Bao for settlement confirmation. | Confirm finance approval, settlement completion, build deposit invoice, and builder start. | High | Open
25 & 25a Citrine Way, Karnup |  |  |  |  | WAITING FOR LANDSCAPER BOOKING CONFIRMATION; OTW TO 2ND PCI |  | PCI2 done

## escalations, money matters
Matter | Last known status | What needs follow-up | Risk | Status
Aseem Goyal refund request | Prior escalation said client hadn’t heard back; later Bao sent a re-engagement email asking if they still wanted to proceed with investing. | This one needs owner review: is it a refund case, reactivation, or both? Check latest thread and reply decisively. | High | Open
Will Oats – engagement fee return / referral | Zaver wanted same-day response using engagement form / lifetime credit-rebate positioning. | Confirm whether Bao actually sent the resolution and whether client accepted. | High | Open / verify
Kevin Griffith – EOI refund | Ethan and Matt had dispute over incorrect account details; on 21 Jan, Zaver said he had already made the payment to the client and asked for reimbursement later. | Confirm reimbursement on internal side, but client-side refund appears actioned. | Medium | Client likely resolved; internal follow-up open
Lot 310 / 340 / 567 / 1022 tranche/invoice items | Some payment-related threads likely resolved, but not all cleanly closed in HubSpot. | Reconcile with accounts so these stop lingering as takeover risk. | Medium | Verify

## check opportunities
Prospect / opportunity | Last known status | What needs follow-up | Risk | Status
Dual Occ up to $1.3m / Lot 857 Pondspice St, Caboolture | Opportunity thread surfaced previously as active. | Confirm if still shopping, finance-ready, or dead. | Medium | Open / verify
Best Value H&L Stockland Estate opportunity | Surfaced as prospecting thread. | Check if proposal was sent and whether client still engaged. | Medium | Open / verify
New Package Stock in WA / Ewan Sprague | Opportunity thread surfaced earlier. | Check if package shortlist was sent and whether still active. | Medium | Open / verify
South Kingsville / brochure for Lot 132 | Brochure/info request thread. | Confirm if converted, inactive, or needs a follow-up. | Low-Medium | Open / verify
Musab Malik strategy brief | Strategy/opportunity thread surfaced. | Confirm next meeting / SOP / finance action. | Medium | Open / verify
Uloopi Vora / Aliraj Raja | Jan thread: SMSF target around ~$700k and personal purchase ~$550k; Bao sent next steps and later “recently sold options.” | Good prospect, but check if finance/rollover happened and whether they advanced. | Medium | Open
Ruswandi | Bao requested updated SOP and re-run numbers with Chris; also asked for updated valuations on other properties. | Confirm whether numbers were rerun and if this is still active. | Medium | Open
Charlotte Niyogakiza | Bao sent SOP request + follow-up meeting invite after a positive call. | Confirm whether SOP came back and meeting occurred. | Low-Medium | Open